## Sheet4
Burndown Chart
Days Into Project | ideal hrs remaining | Actual hrs remaining
1 | 90 | 90
2 | 87 | 89
3 | 84 | 88
4 | 81 | 87
5 | 78 | 84
6 | 75 | 81
7 | 72 | 81
8 | 69 | 81
9 | 66 | 77
10 | 63 | 73
11 | 60 | 72
12 | 57 | 71
13 | 54
14 | 51
15 | 48
16 | 45
17 | 42
18 | 39
19 | 36
20 | 33
21 | 30
22 | 27
23 | 24
24 | 21
25 | 18
26 | 15
27 | 12
28 | 9
29 | 6
30 | 3

## GUI
Log Date | Features | Estimated time to complete features | Actual Time to complete
Visable Board
Visible Kalah pieces
Display current # of stones in pit
Commands for player to make moves
Redraw game state after move
Command line inputs
11/1/17-11/2/17 | Graphic board | 5 | 3
Display winner
2017-11-02 | Welcome display before user starts game | 1 | 2
Displays message if user wants to quit game before it ends
2017-11-03 | difficulty levels displayed | 1 | 1

## BackendServer
Log Date | Features | Estimated time (hr) | Actual hours
2017-11-01 | Array that represents game state | 1 | 2
2017-11-01 | Capture input game state | 1 | 2
2017-11-02 | Ensure rules met before move | 1 | 2
2017-11-02 | Throw error message | 0.5 | 1
2017-11-03 | Updated game state sent to GUI | 0.5 | 1
2017-11-03 | END state | 0.5 | 1
2017-11-03 | array to keep track of seeds | 0.5 | 1

## AI
Log Date | Features | Estimation of hours needed | Remaining hours of Backlog Item | Total
| alpha-beta pruning | 2 |  | 20
| min-max tree | 2
| Computer looks ahead 1 move in tree | 1
| Iterative deepening | 5