## Sheet4
Days Into Project | ideal hrs remaining | Estimated hrs remaining
1 | 90 | 90
2 | 87 | 89
3 | 84 | 88
4 | 81 | 87
5 | 78 | 84
6 | 75 | 81
7 | 72 | 81
8 | 69 | 81
9 | 66 | 77
10 | 63 | 73
11 | 60 | 72
12 | 57 | 71
13 | 54 | 70
14 | 51 | 68
15 | 48 | 64
16 | 45 | 62
17 | 42 | 59
18 | 39 | 57
19 | 36 | 56
20 | 33
21 | 30
22 | 27
23 | 24
24 | 21
25 | 18
26 | 15
27 | 12
28 | 9
29 | 6
30 | 3

## GUI
Features | Estimated time to complete features | Actual Time to complete
Visable Board | 2 | 1
Display current # of stones in pit | 2 | 1
Buttons for player to make moves | 2 | 2
Redraw game state after move | 2 | 2
Command line inputs | 1
Graphic board | 5 | 3
Display winner | 1
Welcome display before user starts game | 1 | 2
Displays message if user wants to quit game before it ends | 1
Difficulty levels displayed | 1 | 1
Display Timer | 1

## BackendServer
Log Date | Features | Estimated time (hr) | Actual hours
2017-11-01 | Array that represents game state | 1 | 2
2017-11-01 | Capture input game state | 1 | 2
2017-11-02 | Ensure rules met before move | 1 | 2
2017-11-02 | Throw error message | 0.5 | 1
2017-11-03 | Updated game state sent to GUI | 0.5 | 1
2017-11-03 | END state | 0.5 | 1
2017-11-03 | array to keep track of seeds | 0.5 | 1
| Data server | 3 | 2
Client server-AI
Client server-non AI

## AI
Features | Estimation of hours needed | Actual hours taken for Backlog Item
alpha-beta pruning | 2 | 2
min-max tree | 2 | 3
Computer looks ahead 1 move in tree | 1 | 1
Iterative deepening | 5